# Business Analyst - Detailed Assignment Document

# Project: Restaurant Management System

BA Name: [To Be Assigned]

Reporting To: Project Manager / Product Owner

Project Duration: 14-18 months

BA Role Duration: Throughout project (with varying intensity)

# Overview

As the Business Analyst on this project, you will be the bridge between business stakeholders (restaurant owners, managers, waiters, customers) and the technical team (developers, QA, DevOps). Your primary responsibility is to ensure that what gets built actually solves real problems and meets user needs.

# Phase 1: Requirements Gathering & Analysis (Weeks 1-4)

## Week 1: Project Orientation & Planning

### Tasks:

Kickoff Meeting

Attend project kickoff with PM, Tech Lead, UI/UX Designer

Understand business objectives and vision

Review competitive analysis (PetPooja, Toast POS, etc.)

Understand our differentiators

Stakeholder Identification

Create stakeholder map

Identify primary stakeholders (restaurant owners, managers)

Identify secondary stakeholders (waiters, chefs, customers)

Schedule interviews (aim for 10-15 stakeholders)

Research & Preparation

Study PetPooja feature list

Research restaurant industry pain points

Review technical requirements document (provided)

Prepare interview questionnaires

### Deliverables:

Stakeholder map

Interview schedule

Interview questionnaires (separate for each role)

Project understanding document

## Week 2-3: Stakeholder Interviews & Observation

### Tasks:

1. Conduct Interviews (2-3 per day)

Interview restaurant owners (5-6 people)

Interview restaurant managers (3-4 people)

Interview waiters (3-4 people)

Interview kitchen staff (2-3 people)

Interview cashiers (2 people)

Interview customers (conduct surveys + 5-6 in-depth interviews)

2. Shadow Restaurant Operations

Spend 1-2 full days at different types of restaurants:

Fine dining

Casual dining

Quick service restaurant (QSR)

Cloud kitchen

### Observe workflows:

Table booking process

Order taking (waiter manual entry)

Kitchen operations (KOT flow)

Table service

Billing and payment

Aggregator order handling (Zomato, Swiggy)

Document pain points

3. Competitive Analysis

Hands-on trial of PetPooja (if possible)

Trial other competitors (Toast POS, Square, Lightspeed)

Document strengths and gaps

### Deliverables:

Interview notes (transcribed)

Pain point summary document

As-Is process maps (how restaurants currently operate)

Competitive analysis report

Photo/video documentation of current workflows

## Week 4: Synthesis & Documentation

### Tasks:

1. Analyze Findings

Identify common patterns across interviews

Categorize pain points by severity and frequency

Map pain points to proposed features

Identify "must-have" vs "nice-to-have" features

2. Create Business Requirements Document (BRD)

Executive summary

Business objectives

Stakeholder analysis

Current state analysis (pain points)

Proposed solution overview

Scope (in-scope, out-of-scope)

Success criteria and KPIs

Assumptions and constraints

High-level timelines

3. Prioritization Workshop

Conduct MoSCoW prioritization with stakeholders

Must Have

Should Have

Could Have

Won't Have (this time)

Document rationale for prioritization decisions

### Deliverables:

Business Requirements Document (BRD) - v1.0

Prioritization matrix

Feature roadmap (aligned with development phases)

# Phase 2: Functional Requirements & Process Design (Weeks 5-8)

## Week 5-6: To-Be Process Design

### Tasks:

Design Optimized Workflows

Create To-Be process maps for each workflow:

Customer Journey: Discovery → Booking → Arrival → QR Scan → Ordering → Tracking → Payment → Feedback

Waiter Journey: Table assignment → Order taking → Service → Billing

Kitchen Journey: Receive order → Prep → Cook → Ready → Served

Manager Journey: Shift start → Monitor operations → Handle issues → Day close

Identify automation opportunities

Validate with stakeholders

Business Rules Documentation

### Define business logic for:

Table booking rules (min duration, buffer time, cancellation policy)

QR refresh logic (1-min cycle, location validation)

Kitchen queue prioritization algorithm

Discount approval workflow

Inventory auto-consumption rules

Commission calculation for aggregators

Loyalty point accrual and redemption

Document edge cases and exceptions

Data Requirements

### Identify all data entities:

Restaurant, Outlet, Table, Booking, Customer, Order, Menu Item, Ingredient, etc.

Define attributes for each entity

Document data validation rules

Identify data sources (user input, third-party APIs, calculations)

### Deliverables:

To-Be process flow diagrams (all workflows)

Business rules document

Data requirements document

Validation rules matrix

## Week 7-8: Functional Requirements Document (FRD)

### Tasks:

1. Write Detailed Functional Requirements

Document requirements for each module (refer to technical requirements doc) For each feature, specify:

Functional description

User roles involved

Inputs and outputs

Business rules

Validation rules

Error handling

Success criteria

### Example structure for one feature:

# Feature: QR Code Scanning for Menu Access

## FR-001: QR Code Generation

Description: System shall generate unique QR code for each table that refreshes every 1 minute

User Role: System (automated)

Trigger: Table status changes to "Occupied"

### Business Rules:

QR contains table_id, timestamp, and secure token

QR expires after 60 seconds

New QR generated every minute until table status changes

### Validation:

QR must be scannable

QR must encode valid data

Success Criteria: Customer can scan QR and access menu

FR-002: QR Code Scanning

Description: Customer shall be able to scan QR code from mobile app to access digital menu

User Role: Customer (dine-in)

### Preconditions:

Customer must be logged into app

Customer must have camera permission

GPS must be enabled

### Steps:

Customer opens app and taps "Scan QR to Order"

Camera opens with QR scanner

Customer scans QR on table

System validates QR (checks expiry, token)

System validates customer location (must be at restaurant)

If valid, system loads menu interface

If invalid, system shows error message

### Business Rules:

QR must be scanned within 60 seconds of generation

Customer GPS location must be within 100m of restaurant

QR can only be scanned once (invalidated after scan)

### Validation:

GPS coordinates within range

QR not expired

QR not already used

### Error Handling:

"QR expired. Please request new QR from waiter."

"You must be at the restaurant to scan this QR."

"Invalid QR code. Please try again."

Success Criteria: Menu loads within 2 seconds of successful scan

2. UI/UX Requirements

Collaborate with UI/UX designer

### Document UI requirements for each screen:

Screen purpose

Elements (buttons, forms, tables, etc.)

User interactions

Responsive behavior (mobile, tablet, desktop)

Accessibility requirements

3. Integration Requirements

Document integration specs for: Payment gateways (Razorpay, Stripe)

Food aggregators (Zomato, Swiggy)

Accounting software (Tally, QuickBooks)

SMS/Email gateways

Maps API

Storage (AWS S3)

### For each integration:

Purpose

Data exchange (what data goes in/out)

Authentication mechanism

Frequency (real-time, batch, on-demand)

Error handling

Fallback plan if integration fails

4. Non-Functional Requirements

Performance requirements (response times, throughput)

Security requirements (authentication, encryption, compliance)

Scalability requirements (concurrent users, data volume)

Availability requirements (uptime SLA)

Browser/device compatibility

Accessibility (WCAG compliance)

### Deliverables:

Functional Requirements Document (FRD) - comprehensive, 100+ pages

UI/UX requirements document

Integration specifications document

Non-functional requirements document

# Phase 3: Data Modeling & User Stories (Weeks 9-10)

## Week 9: Data Modeling

### Tasks:

1. Create Entity Relationship Diagram (ERD)

Identify all entities (tables in database)

Define relationships (one-to-one, one-to-many, many-to-many)

Define primary keys and foreign keys

Normalize to 3NF (third normal form)

Review with database architect

### Key Entities to Model:

User, Role, Permission

Restaurant, Outlet, Floor, Table

Booking, Waitlist

Customer, CustomerAddress

Menu, Category, MenuItem, MenuItemVariant, Addon

Order, OrderItem, OrderModification

Ingredient, Recipe, RecipeIngredient

PurchaseOrder, Supplier, Stock, StockTransaction

Invoice, Payment, PaymentMethod

Loyalty, LoyaltyTransaction, Reward

Staff, Attendance, Shift

Review, Rating

Notification, EmailLog, SMSLog

Report, ReportSchedule

Integration, APILog

2. Create Data Dictionary

For each entity, document: Table name

Description

Columns (name, data type, length, nullable, default)

Constraints (primary key, foreign key, unique, check)

Indexes

Sample data

### Example:

Table: bookings Description: Stores restaurant table bookings made by customers

### Columns:

booking_id (INT, PK, AUTO_INCREMENT) - Unique booking identifier

restaurant_id (INT, FK → restaurants.restaurant_id, NOT NULL) - Restaurant reference

table_id (INT, FK → tables.table_id, NOT NULL) - Table reference

customer_id (INT, FK → customers.customer_id, NOT NULL) - Customer reference

booking_date (DATE, NOT NULL) - Date of booking

booking_time (TIME, NOT NULL) - Time of booking

party_size (INT, NOT NULL, CHECK > 0) - Number of guests

duration_minutes (INT, DEFAULT 120) - Expected duration

status (ENUM('pending','confirmed','cancelled','completed','no_show'), DEFAULT 'pending')

special_requests (TEXT, NULL) - Customer special requests

deposit_amount (DECIMAL(10,2), DEFAULT 0.00) - Advance payment

payment_status (ENUM('pending','paid','refunded'), DEFAULT 'pending')

created_at (TIMESTAMP, DEFAULT CURRENT_TIMESTAMP)

updated_at (TIMESTAMP, ON UPDATE CURRENT_TIMESTAMP)

### Indexes:

idx_restaurant_date (restaurant_id, booking_date) - For availability queries

idx_customer (customer_id) - For customer booking history

Sample Data: booking_id: 1001 restaurant_id: 5 table_id: 23 customer_id: 789 booking_date: 2026-02-15 booking_time: 19:30:00 party_size: 4 duration_minutes: 120 status: confirmed special_requests: "Window seat if possible, birthday celebration" deposit_amount: 500.00 payment_status: paid

3. Define Data Validation Rules

Input validation (format, length, range)

Business validation (booking date can't be in past)

Cross-field validation (end_time must be after start_time)

Reference validation (customer_id must exist in customers table)

### Deliverables:

Entity Relationship Diagram (ERD) - visual diagram

Data Dictionary - complete specification

Data validation rules matrix

## Week 10: User Stories & Backlog

### Tasks:

1. Write User Stories

Convert each requirement into user stories

Use format: "As a [role], I want [feature], so that [benefit]"

### Write for all user roles:

Super Admin

Restaurant Owner/Admin

Manager Waiter

Chef/Kitchen Staff

Cashier

Customer (dine-in)

Customer (marketplace)

### Example User Stories:

Epic: QR-Based Ordering

US-001: Generate Dynamic QR Codes

As a system

I want to automatically generate unique QR codes for each table that refresh every minute So that customers can securely access the digital menu from their table

### Acceptance Criteria:

QR code is generated when table status changes to "Occupied"

QR code refreshes every 60 seconds

QR code encodes table_id, timestamp, and secure token

QR code is displayed on table screen

Old QR codes are invalidated upon refresh

QR code generation is logged for audit

Priority: High

Story Points: 5

Dependencies: Table management system

US-002: Scan QR Code to Access Menu

As a dine-in customer

I want to scan the QR code on my table using the mobile app So that I can view the digital menu and place my order

### Acceptance Criteria:

Customer can access QR scanner from app home screen

App requests camera permission if not granted

QR scanner opens with clear instructions

System validates QR code (not expired, not used)

System validates customer location (within 100m of restaurant)

If valid, digital menu loads within 2 seconds

If invalid, clear error message is shown

QR code is marked as used after successful scan

Customer cannot scan same QR again (one-time use)

Priority: High

Story Points: 8

Dependencies: QR generation, GPS location service, Menu API

### Error Scenarios:

"QR code expired. Please request a new one from your waiter."

"You must be at the restaurant to scan this QR."

"Camera permission required to scan QR."

"Network error. Please check your internet connection."

2. Story Pointing (Estimation)

Conduct planning poker sessions with dev team

Estimate complexity in story points (Fibonacci: 1, 2, 3, 5, 8, 13, 21)

### Factor in:

Technical complexity

Uncertainty/unknowns

Dependencies

Testing effort

3. Backlog Prioritization

Work with Product Owner to prioritize backlog

### Use MoSCoW method:

Must Have (for MVP)

Should Have (Phase 2) Could Have (Phase 3+)

Won't Have (future or never)

### Consider:

Business value

Technical dependencies Risk

Effort

4. Create Epics

Group related user stories into epics

### Examples of epics:

Table Management

QR-Based Ordering

Kitchen Display System

Payment Processing

Inventory Management

CRM & Loyalty

Marketplace

Aggregator Integration

White-Label Platform

### Deliverables:

Complete backlog (150-250 user stories)

Epic breakdown

Story point estimates

Prioritized backlog (ready for Sprint 1)

# Phase 4: Wireframe Review & Validation (Weeks 11-12)

## Tasks:

1. Collaborate with UI/UX Designer

Review wireframes for each screen

Ensure alignment with requirements

Validate user flows

### Check for:

Missing screens

Incorrect flows

Accessibility issues

Responsive design considerations

2. Annotate Wireframes

Add functional annotations to wireframes

### Specify:

Field validations

Button actions

Conditional display logic

Error states

Empty states

Loading states

### Example Annotation:

Screen: Customer - Book Table

### Date Picker:

Default: Today's date

Min: Today

Max: 30 days from today

Validation: Cannot select past dates

Error: "Please select a valid date"

### Time Selector:

Display: Restaurant operating hours only

Intervals: 15 minutes

Validation: Time must be at least 1 hour from now

Conditional: If selected time is within 1 hour, show "Call restaurant for immediate booking"

### Party Size:

Input: Number (1-20)

Default: 2

Validation: Must be positive integer

Conditional: If > 10, show "For large groups, please call restaurant"

### Floor Plan:

Display: Interactive floor plan

Filter: Only show tables matching party size ±2

### Color Coding:

Green: Available

Yellow: Booked (show vacancy time)

Red: Occupied

Gray: Not available for booking

On Click: Show table details (number, capacity, location, price if any)

3. User Flow Validation

Walk through each user journey

Ensure smooth navigation

Identify potential UX issues

Document improvements

4. Stakeholder Review

Present wireframes to stakeholders

Gather feedback

Document change requests

Prioritize changes

### Deliverables:

Annotated wireframes

User flow diagrams

Wireframe review feedback document

UX improvement recommendations

# Phase 5: Sprint Planning & Execution Support (Weeks 13+)

## Ongoing Tasks During Development:

1. Sprint Planning (Every 2 Weeks)

### Pre-Sprint:

Refine user stories for upcoming sprint

Ensure acceptance criteria are clear

Clarify any ambiguities with dev team

Prepare for sprint planning meeting

### During Sprint Planning:

Present user stories to team

Answer questions

Help with estimation

Ensure team understands requirements

### Post-Sprint Planning:

Document sprint goals

Update backlog

2. Daily Standups (15 min daily)

Attend standups

Listen for blockers related to requirements

Clarify requirements if needed

Note any scope creep

3. Backlog Refinement (Weekly)

Review upcoming stories

Break down large stories (epics)

Add acceptance criteria

Prioritize with Product Owner

Remove/archive completed stories

4. Requirements Clarification (Ad-hoc)

Answer developer questions

Provide mockups or examples

Update FRD if needed

Document decisions

5. Sprint Review/Demo (Every 2 Weeks)

Attend sprint demo

Validate delivered features against acceptance criteria

Provide feedback to team

Gather stakeholder feedback

Document any changes needed

6. Sprint Retrospective (Every 2 Weeks)

Participate in retro

Share insights on requirements process

Identify improvements

# Phase 6: Testing & Quality Assurance (Parallel to Development)

## Tasks:

1. Test Case Writing (Ongoing)

Write test cases for each user story

### Include:

Test case ID

User story reference

Preconditions

Test steps

Expected results

Actual results (filled by QA)

Pass/Fail status

### Example Test Case:

Test Case ID: TC-QR-001

User Story: US-002 (Scan QR Code to Access Menu)

Module: QR-Based Ordering

Priority: High

### Precondition:

Customer app is installed and user is logged in

Camera permission is granted

GPS is enabled

Customer is at restaurant (within 100m)

QR code is displayed on table

### Test Steps:

Open customer app

Tap "Scan QR to Order" button

Point camera at table QR code

Wait for scan to complete

### Expected Result:

QR scanner opens

QR code is recognized

Location validation passes

Digital menu loads within 2 seconds

Menu displays all categories and items

### Test Data:

Restaurant ID: 101

Table ID: 5

QR Code: [sample QR data]

Actual Result: [To be filled by QA]

Status: [Pass/Fail]

Comments: [Any issues found]

2. User Acceptance Testing (UAT) Planning

Create UAT plan

Define UAT scope (features to test)

Identify UAT participants (real users)

Schedule UAT sessions

Prepare UAT scripts (step-by-step instructions)

Create UAT environment (staging)

Prepare test data

3. UAT Execution

Conduct UAT sessions

Observe users

Note pain points

Document bugs/issues

Gather feedback

Create bug reports

Prioritize fixes

4. Regression Testing Support

Maintain regression test suite

Update test cases when requirements change

Review regression test results

Sign off on releases

# Phase 7: Integration & Documentation (Parallel to Development)

## Tasks:

1. Integration Specification (As Needed)

Work with third-party vendors

### Document integration requirements:

Zomato API integration

Swiggy API integration

Razorpay/Stripe integration

Tally integration

SMS/Email gateway

Google Maps API

Define data mapping

Create sample requests/responses

Document error scenarios

Review integration contracts

2. API Documentation Review

Review developer-created API docs

Ensure completeness

Validate against requirements

Test API endpoints (using Postman)

Document API use cases

3. User Manual Creation (Collaborate with Tech Writer)

Outline user manual structure

Provide functional descriptions

Review drafts

Validate screenshots and steps

Ensure accuracy

# Phase 8: Go-Live Support & Handoff (Final Weeks)

## Tasks:

1. Go-Live Checklist

Verify all MVP features are complete

Ensure UAT sign-off

Review deployment plan

Validate production environment

Confirm data migration (if any)

Review rollback plan

Ensure support team is trained

2. Pilot Program Support

Onboard pilot restaurants

Conduct training sessions

Gather feedback

Monitor usage

Document issues Create improvement backlog

3. Post-Launch Monitoring (First 2-4 Weeks)

Monitor system usage

Track KPIs

Gather user feedback

Prioritize bug fixes

Identify usability issues

Create Phase 2 backlog

4. Handoff Documentation

Update all documents with as-built details

Create knowledge transfer document

Train support team

Document FAQs

Create troubleshooting guide

# Deliverables Summary

## Documents to Create:

Stakeholder Map

Interview Notes & Pain Point Summary

As-Is Process Maps

Competitive Analysis Report

Business Requirements Document (BRD)

Prioritization Matrix

To-Be Process Flow Diagrams

Business Rules Document 9.  Data Requirements Document

Functional Requirements Document (FRD)

UI/UX Requirements Document

Integration Specifications

Non-Functional Requirements

Entity Relationship Diagram (ERD)

Data Dictionary

Data Validation Rules Matrix

User Stories (150-250)

Epic Breakdown

Prioritized Backlog

Annotated Wireframes

User Flow Diagrams

Test Cases (500-1000)

UAT Plan & Scripts

Requirements Traceability Matrix (RTM)

Change Request Log

Sprint Documentation (ongoing)

Go-Live Checklist

Knowledge Transfer Document

# Tools You'll Use

## Documentation:

Confluence - Wiki for all documentation

Google Docs - Collaborative editing

Microsoft Word - Formal documents (BRD, FRD)

## Process Mapping:

Lucidchart - Process flows, user journeys

Miro - Collaborative workshops

Draw.io - Free alternative

## Data Modeling:

dbdiagram.io - ERD creation

MySQL Workbench - Database design

ERDPlus - Free ERD tool

## Requirements Management:

Jira - User stories, backlog, sprint planning

Confluence - Linked to Jira for documentation Excel/Google Sheets - Traceability matrix

## Wireframe Review:

Figma - View and comment on designs

InVision - Interactive prototypes

## Testing:

Jira/TestRail - Test case management

Excel - Test case sheets

## Communication:

Slack/Microsoft Teams - Daily communication

Zoom - Meetings and workshops

Email - Formal communication

# Success Criteria for BA

## By End of Phase 1 (Month 1):

BRD approved by stakeholders

10+ stakeholder interviews completed

Pain points documented

## By End of Phase 2 (Month 2):

FRD completed (100+ pages)

ERD finalized

Data dictionary completed

Integration specs documented

## By End of Phase 3 (Month 3):

150+ user stories written

Sprint 1-3 backlog ready

Wireframes validated

## Ongoing (Throughout Project):

95%+ user stories meet acceptance criteria in first attempt

< 5% scope creep per sprint

All requirements questions answered within 24 hours

Zero critical defects due to requirement gaps

UAT pass rate > 90%

Stakeholder satisfaction score > 4/5

# Tips for Success

## 1. Ask "Why" Multiple Times

Don't just document what users say they want

### Understand the underlying problem Example:

User: "I want a report showing all orders"

BA: "Why do you need that?"

User: "To see sales performance"

BA: "Why sales performance?"

User: "To identify slow-moving items"

BA: "Why identify slow-moving items?"

User: "To reduce wastage and optimize inventory"

Real requirement: Inventory optimization based on demand patterns

## 2. Think Like an End User

Don't just write requirements from a technical perspective

Put yourself in the shoes of each user role

Think about their goals, frustrations, and context

## 3. Be Visual

Use diagrams, flowcharts, mockups wherever possible

A picture is worth a thousand words

Developers understand visuals better than long paragraphs

## 4. Document Decisions

Every decision made should be documented

### Include:

What was decided

Why it was decided

Who made the decision

When it was decided

What alternatives were considered

## 5. Validate Early and Often

Don't wait until the end to validate requirements

Show wireframes early

Conduct frequent demos

Gather feedback continuously

## 6. Manage Scope Creep

Document all change requests

Assess impact on timeline, cost, resources

Get approval before committing to changes

Keep a log of approved/rejected changes

## 7. Be the Bridge

Translate business language to technical language

Translate technical language to business language

Ensure both sides understand each other

## 8. Test Your Requirements

Can a developer build it based on your requirements alone?

Can a QA engineer test it based on your acceptance criteria?

If not, your requirements need more detail

# Common Pitfalls to Avoid

Writing vague requirements ("System should be fast")

Instead: "API response time should be < 200ms for 95% of requests"

Assuming knowledge ("Everyone knows how restaurant billing works")  Instead: Document every detail, assume no prior knowledge

Ignoring edge cases (Only documenting happy path)

Instead: Think of all possible scenarios (errors, failures, edge cases)

Over-designing (Trying to solve every problem in v1)

Instead: Focus on MVP, keep future enhancements in backlog

Not involving stakeholders (Writing requirements in isolation)

Instead: Constant communication, validation, feedback loops

Changing requirements mid-sprint (Without impact analysis)

Instead: Follow change control process, assess impact

Writing technical specifications (That's developer's job)

Instead: Write what needs to be built, not how to build it

Not updating documentation (As requirements change)

Instead: Keep all docs updated, maintain single source of truth

# Recommended Reading

## Books:

"User Stories Applied" by Mike Cohn

"Software Requirements" by Karl Wiegers

"The Lean Startup" by Eric Ries

"Don't Make Me Think" by Steve Krug (UX)

## Online Resources:

IIBA (International Institute of Business Analysis) BABOK Guide

Scrum Guide (scrum.org)

Atlassian Agile Coach (for Jira, Confluence)

## Industry Knowledge:

Restaurant industry blogs

POS system reviews

Hospitality technology forums

# Weekly Time Allocation (Typical)

### Weeks 1-4 (Requirements Phase):

Stakeholder interviews: 40%

Documentation: 30%

Research: 20% Meetings: 10%

### Weeks 5-12 (FRD & Design):

Writing FRD: 40%

Wireframe review: 20% Data modeling: 20%

Stakeholder validation: 10%

Meetings: 10%

### Weeks 13+ (Development Phase):

Sprint planning/backlog refinement: 30%

Requirements clarification: 25%

Testing (writing test cases, UAT): 25%

Documentation updates: 10%

Meetings (standup, review, retro): 10%

# Your First Week Action Plan

## Day 1:

Attend project kickoff meeting

Set up tools (Jira, Confluence, Lucidchart accounts)

Read technical requirements document (this doc!)

Create stakeholder map

## Day 2:

Research PetPooja and competitors

Create interview questionnaires

Schedule stakeholder interviews (aim for 15)

Start BRD outline

## Day 3:

Conduct 2-3 stakeholder interviews

Shadow a restaurant (half day)

Document initial findings

## Day 4:

Conduct 2-3 more interviews

Review competitor features

Start as-is process mapping

## Day 5:

Synthesis session (analyze interview data)

Document pain points

Present initial findings to team

Plan for Week 2

Remember: You are the voice of the user. Your job is to ensure the right product gets built, not just any product. Be thorough, be curious, and always ask "why."

Good luck!